## Requirements Traceability
Requirement ID | Requirement Name | Module | Test Scenario ID | Test Case ID | Test Case Summary | Coverage Status | Priority | Severity | Implementation Status | Notes
FR-UPLOAD-001 | Single file upload capability | Upload | TS-UP-001 | TC_CENTRAL_001 | Admin uploads single PDF file | Covered | P1 | Critical | Complete | Happy path - file upload
FR-UPLOAD-001 | Single file upload capability | Upload | TS-UP-001 | TC_CENTRAL_002 | File appears in document list | Covered | P1 | Critical | Complete | Verify upload display
FR-UPLOAD-002 | Category selection on upload | Upload | TS-UP-002 | TC_CENTRAL_007 | Category dropdown available | Covered | P1 | High | Complete | 5 categories available
FR-UPLOAD-003 | File size validation | Upload | TS-UP-003 | TC_CENTRAL_021 | Reject files > 10 MB | Covered | P1 | Critical | Complete | Size limit enforcement
FR-UPLOAD-004 | Multi-file upload support | Upload | TS-UP-004 | TC_CENTRAL_008 | Multiple file selection | Covered | P2 | High | Complete | Batch upload capability
FR-UPLOAD-005 | File type validation | Upload | TS-UP-005 | TC_CENTRAL_031 | Reject .exe files | Covered | P1 | Critical | Complete | Security - malware prevention
FR-DOWNLOAD-001 | Authorized file download | Download | TS-DOWN-001 | TC_CENTRAL_003 | Admin downloads file | Covered | P1 | Critical | Complete | Happy path - download
FR-DOWNLOAD-002 | Download count tracking | Download | TS-DOWN-002 | TC_CENTRAL_026 | Download counter increments | Covered | P1 | High | Complete | Track download usage
FR-DOWNLOAD-003 | Download limit enforcement | Download | TS-DOWN-003 | TC_CENTRAL_027 | Enforce 50 download limit | Covered | P1 | Critical | Complete | Resource protection
FR-DOWNLOAD-004 | Bulk download as ZIP | Download | TS-DOWN-004 | TC_CENTRAL_028 | Download multiple files | Covered | P2 | High | Complete | Convenience feature
FR-DOWNLOAD-005 | QR code download link | Download | TS-DOWN-005 | TC_CENTRAL_055 | QR download without login | Covered | P2 | High | Complete | Supplier access
FR-DELETE-001 | Soft delete with confirmation | Delete | TS-DEL-001 | TC_CENTRAL_004 | Delete confirmation dialog | Covered | P1 | Critical | Complete | Safety - confirm before delete
FR-DELETE-002 | File removal from view | Delete | TS-DEL-002 | TC_CENTRAL_091 | File removed from list | Covered | P1 | Critical | Complete | Soft delete marker
FR-DELETE-003 | Audit log deletion entry | Delete | TS-DEL-003 | TC_CENTRAL_095 | Deletion recorded in audit | Covered | P1 | High | Complete | Compliance - audit trail
FR-DELETE-004 | Admin file restore | Delete | TS-DEL-004 | TC_CENTRAL_093 | Restore deleted file | Covered | P2 | High | Complete | Undo capability
FR-DELETE-005 | 90-day retention policy | Delete | TS-DEL-005 | TC_CENTRAL_094 | Permanent deletion after 90 days | Covered | P2 | Medium | Complete | Data lifecycle
FR-LIST-001 | Display file metadata columns | List | TS-LIST-001 | TC_CENTRAL_002 | File displays with all columns | Covered | P1 | Critical | Complete | Data completeness
FR-LIST-002 | Pagination support | List | TS-LIST-002 | TC_CENTRAL_006 | Pagination with default 10 items | Covered | P1 | High | Complete | Performance - large datasets
FR-LIST-003 | File size display | List | TS-LIST-003 | TC_CENTRAL_003 | Size column shows file size | Covered | P1 | High | Complete | Information completeness
FR-LIST-004 | Upload date/time display | List | TS-LIST-004 | TC_CENTRAL_004 | Date column shows upload date | Covered | P1 | High | Complete | Timestamp accuracy
FR-LIST-005 | Uploader name display (not email) | List | TS-LIST-005 | TC_CENTRAL_005 | Shows user name not email | Covered | P1 | High | Complete | Privacy protection
FR-LIST-006 | Sort functionality | List | TS-LIST-006 | TC_CENTRAL_012 | Sort by multiple columns | Covered | P2 | High | Complete | Usability feature
FR-LIST-007 | Filter by date range | List | TS-LIST-007 | TC_CENTRAL_017 | Date range filtering | Covered | P2 | High | Complete | Search capability
FR-LIST-008 | Soft-deleted file exclusion | List | TS-LIST-008 | TC_CENTRAL_092 | Deleted files not in list | Covered | P1 | High | Complete | Data integrity
FR-PERM-001 | Admin full access | Permission | TS-PERM-001 | TC_CENTRAL_071 | Admin upload/download/delete | Covered | P1 | Critical | Complete | Role-based access
FR-PERM-002 | AHM assigned moulds | Permission | TS-PERM-002 | TC_CENTRAL_010 | AHM accesses assigned mould | Covered | P1 | Critical | Complete | Scoping by role
FR-PERM-003 | Client download-only | Permission | TS-PERM-003 | TC_CENTRAL_073 | Client cannot upload/delete | Covered | P1 | Critical | Complete | Read-only access
FR-PERM-004 | Client mould filtering | Permission | TS-PERM-004 | TC_CENTRAL_024 | Client sees only assigned mould | Covered | P1 | Critical | Complete | Data isolation
FR-PERM-005 | Supplier QR access | Permission | TS-PERM-005 | TC_CENTRAL_059 | Supplier downloads via QR | Covered | P1 | Critical | Complete | Supplier workflow
FR-PERM-006 | Unauthorized 403 error | Permission | TS-PERM-006 | TC_CENTRAL_076 | Invalid role returns 403 | Covered | P1 | Critical | Complete | Security - access denial
FR-PERM-007 | Session timeout protection | Permission | TS-PERM-007 | TC_CENTRAL_027 | Deactivated user denied | Covered | P1 | High | Complete | Session management
FR-VALID-001 | 10 MB file size limit | Validation | TS-VALID-001 | TC_CENTRAL_021 | Reject files > 10 MB | Covered | P1 | Critical | Complete | Resource protection
FR-VALID-002 | File type restrictions | Validation | TS-VALID-002 | TC_CENTRAL_031 | Reject .exe files | Covered | P1 | Critical | Complete | Security validation
FR-VALID-003 | Empty file rejection | Validation | TS-VALID-003 | TC_CENTRAL_033 | Reject 0-byte files | Covered | P1 | High | Complete | Data quality
FR-VALID-004 | Category required field | Validation | TS-VALID-004 | TC_CENTRAL_038 | Category field mandatory | Covered | P1 | High | Complete | Form validation
FR-VALID-005 | No file selected error | Validation | TS-VALID-005 | TC_CENTRAL_040 | Error when no file selected | Covered | P1 | High | Complete | Input validation
FR-VALID-006 | Duplicate filename handling | Validation | TS-VALID-006 | TC_CENTRAL_041 | Allow/prevent duplicates | Covered | P2 | Medium | Complete | Naming policy
FR-VALID-007 | Unicode filename support | Validation | TS-VALID-007 | TC_CENTRAL_023 | Unicode filenames accepted | Covered | P2 | Medium | Complete | Internationalization
FR-VALID-008 | SQL injection prevention | Validation | TS-VALID-008 | TC_CENTRAL_040 | Prevent SQL injection | Covered | P1 | Critical | Complete | Security - input sanitization
FR-VALID-009 | XSS prevention | Validation | TS-VALID-009 | TC_CENTRAL_045 | Prevent XSS attacks | Covered | P1 | Critical | Complete | Security - output encoding
FR-CAT-001 | 5 categories defined | Category | TS-CAT-001 | TC_CENTRAL_007 | 5 categories available | Covered | P1 | High | Complete | Feature definition
FR-CAT-002 | Category immutability | Category | TS-CAT-002 | TC_CENTRAL_042 | Category cannot change after upload | Covered | P1 | High | Complete | Data consistency
FR-CAT-003 | Category count display | Category | TS-CAT-003 | TC_CENTRAL_014 | Tab shows file count | Covered | P1 | High | Complete | UI feedback
FR-CAT-004 | Legacy category mapping | Category | TS-CAT-004 | TC_CENTRAL_024 | Legacy data mapped to new categories | Covered | P2 | Medium | Complete | Migration support
FR-QR-001 | QR code generation | QR Code | TS-QR-001 | TC_CENTRAL_055 | Generate QR on upload | Covered | P2 | High | Complete | Supplier feature
FR-QR-002 | QR code resolution | QR Code | TS-QR-002 | TC_CENTRAL_056 | Scan QR to download | Covered | P2 | High | Complete | External access
FR-QR-003 | QR expiration | QR Code | TS-QR-003 | TC_CENTRAL_057 | QR expires after link expiry | Covered | P2 | Medium | Complete | Security - time-limited access
FR-QR-004 | QR icon in list | QR Code | TS-QR-004 | TC_CENTRAL_006 | QR icon visible in document list | Covered | P2 | High | Complete | UI feature
FR-SEARCH-001 | Search by filename | Search | TS-SEARCH-001 | TC_CENTRAL_005 | Find file by name | Covered | P2 | High | Complete | Search capability
FR-SEARCH-002 | Filter by date range | Search | TS-SEARCH-002 | TC_CENTRAL_017 | Filter by upload date | Covered | P2 | High | Complete | Advanced filtering
FR-SEARCH-003 | Filter by uploader | Search | TS-SEARCH-003 | TC_CENTRAL_018 | Filter by user who uploaded | Covered | P2 | High | Complete | Advanced filtering
FR-SEARCH-004 | Search performance <1s | Search | TS-SEARCH-004 | TC_CENTRAL_064 | Search completes in <1 second | Covered | P2 | High | Complete | Performance SLA
FR-MODAL-001 | Modal drag-and-drop | Modal | TS-MODAL-001 | TC_CENTRAL_090 | Drag and drop file upload | Covered | P2 | Medium | Complete | UX enhancement
FR-MODAL-002 | Upload progress bar | Modal | TS-MODAL-002 | TC_CENTRAL_090 | Show upload progress | Covered | P2 | Medium | Complete | UX feedback
FR-MODAL-003 | Cancel button | Modal | TS-MODAL-003 | TC_CENTRAL_011 | Cancel closes modal | Covered | P2 | High | Complete | User control
FR-MODAL-004 | File preview | Modal | TS-MODAL-004 | TC_CENTRAL_001 | Preview selected file | Covered | P2 | Medium | Complete | UX enhancement
NFR-PERF-001 | Upload SLA <=30 seconds | Performance | TS-PERF-001 | TC_CENTRAL_061 | Upload completes in <=30s | Covered | P2 | High | Complete | Performance SLA
NFR-PERF-002 | Search SLA <1 second | Performance | TS-PERF-002 | TC_CENTRAL_064 | Search returns in <1s | Covered | P2 | High | Complete | Performance SLA
NFR-PERF-003 | List load <2 seconds | Performance | TS-PERF-003 | TC_CENTRAL_063 | Document list loads in <2s | Covered | P2 | High | Complete | Performance SLA
NFR-PERF-004 | QR generation <2 seconds | Performance | TS-PERF-004 | TC_CENTRAL_065 | QR generates in <2s | Covered | P2 | Medium | Complete | Performance SLA
NFR-SCALE-001 | Concurrent user support | Scalability | TS-SCALE-001 | TC_CENTRAL_068 | 10 concurrent users | Covered | P2 | High | Complete | Load testing
NFR-SCALE-002 | 10K documents support | Scalability | TS-SCALE-002 | TC_CENTRAL_070 | Support up to 10K files | Covered | P2 | High | Complete | DB scalability
NFR-SCALE-003 | Lazy QR backfill | Scalability | TS-SCALE-003 | TC_CENTRAL_066 | Generate QR on demand | Covered | P2 | Medium | Complete | Performance optimization
NFR-SECURITY-001 | HTTPS/TLS encryption | Security | TS-SEC-001 | TC_CENTRAL_078 | All connections encrypted | Covered | P1 | Critical | Complete | Transport security
NFR-SECURITY-002 | CSRF protection | Security | TS-SEC-002 | TC_CENTRAL_077 | CSRF tokens on forms | Covered | P1 | Critical | Complete | Attack prevention
NFR-SECURITY-003 | SQL injection prevention | Security | TS-SEC-003 | TC_CENTRAL_040 | Parameterized queries | Covered | P1 | Critical | Complete | Injection prevention
NFR-SECURITY-004 | XSS prevention | Security | TS-SEC-004 | TC_CENTRAL_045 | Output encoding | Covered | P1 | Critical | Complete | Injection prevention
NFR-SECURITY-005 | Malware file rejection | Security | TS-SEC-005 | TC_CENTRAL_031 | Block .exe and malware | Covered | P1 | Critical | Complete | File type validation
NFR-SECURITY-006 | Unauthorized user 403 | Security | TS-SEC-006 | TC_CENTRAL_076 | Return 403 Forbidden | Covered | P1 | Critical | Complete | Access control
NFR-AUDIT-001 | Audit log all actions | Audit | TS-AUD-001 | TC_CENTRAL_095 | Log upload/download/delete | Covered | P1 | Critical | Complete | Compliance
NFR-AUDIT-002 | Audit immutable | Audit | TS-AUD-002 | TC_CENTRAL_096 | Audit logs cannot be modified | Covered | P1 | Critical | Complete | Compliance
NFR-AUDIT-003 | Timestamp accuracy | Audit | TS-AUD-003 | TC_CENTRAL_048 | ISO 8601 timestamps | Covered | P1 | High | Complete | Data integrity
NFR-AUDIT-004 | User identification | Audit | TS-AUD-004 | TC_CENTRAL_005 | Show user name in logs | Covered | P1 | High | Complete | Accountability
NFR-INTEGRITY-001 | No orphan files | Integrity | TS-INT-001 | TC_CENTRAL_097 | Verify file-record match | Covered | P2 | High | Complete | Data consistency
NFR-INTEGRITY-002 | Soft delete audit trail | Integrity | TS-INT-002 | TC_CENTRAL_091 | Mark deleted, keep backup | Covered | P1 | High | Complete | Data recovery
NFR-INTEGRITY-003 | 90-day retention | Integrity | TS-INT-003 | TC_CENTRAL_094 | Keep data 90 days post-delete | Covered | P2 | Medium | Complete | Data lifecycle
NFR-INTEGRITY-004 | Atomicity in transactions | Integrity | TS-INT-004 | TC_CENTRAL_098 | All or nothing operations | Covered | P1 | High | Complete | ACID compliance
NFR-INTEGRITY-005 | Backup integrity | Integrity | TS-INT-005 | TC_CENTRAL_099 | Verify backup completeness | Covered | P2 | Medium | Complete | DR capability
NFR-A11Y-001 | Keyboard navigation | Accessibility | TS-A11Y-001 | TC_CENTRAL_084 | All functions accessible via keyboard | Covered | P2 | Medium | Complete | WCAG AA
NFR-A11Y-002 | Screen reader support | Accessibility | TS-A11Y-002 | TC_CENTRAL_085 | Screen reader compatible | Covered | P2 | Medium | Complete | WCAG AA
NFR-A11Y-003 | Color contrast WCAG AA | Accessibility | TS-A11Y-003 | TC_CENTRAL_086 | Contrast ratio >= 4.5:1 | Covered | P2 | High | Complete | WCAG AA
NFR-COMPAT-001 | Responsive design | Compatibility | TS-COMPAT-001 | TC_CENTRAL_081 | Works on mobile/tablet/desktop | Covered | P2 | Medium | Complete | Responsive
NFR-COMPAT-002 | Cross-browser support | Compatibility | TS-COMPAT-002 | TC_CENTRAL_083 | Chrome, Firefox, Safari, Edge | Covered | P2 | Medium | Complete | Browser compatibility
NFR-I18N-001 | Unicode filename support | I18N | TS-I18N-001 | TC_CENTRAL_023 | Filenames in multiple languages | Covered | P2 | Medium | Complete | Globalization
NFR-I18N-002 | RTL language support | I18N | TS-I18N-002 | TC_CENTRAL_087 | Right-to-left layout | Covered | P3 | Low | Complete | Globalization